## DASHBOARD
KINETIC CRM - PROJECT PROGRESS TRACKER
Enterprise CRM System ¦ Timeline: 3 Juni - 31 Juli 2026 (Revisi: 22 Juni) ¦ Status: Minggu ke-1 (Restart)
Metodologi: Source Code Audit ¦ Generated: 29 Juni 2026
TIMELINE: Juni 3 ---[REVISI]--- Juni 22 ==================== Juli 31
Original Start: 3 Jun ¦ Restart: 22 Jun ¦ Days Active: 7/30 ¦ Progress: 38% ¦ Status: EARLY STAGE
35% |  |  | 23% |  |  | 20
TOTAL PROGRESS |  |  | TIME ELAPSED |  |  | TOTAL MODUL
3 |  | 12 |  | 5 |  | 42/104 |  | 0%
Selesai |  | Dalam Proses |  | Belum Mulai |  | Task Done |  | Backend
PROGRESS PER MINGGU (Berdasarkan Git Log)
Minggu |  | Tanggal |  | Deskripsi |  | Planned | Actual | Status
W0 |  | 3-21 Jun |  | Old project (revisi) - NOT counted |  | 0% | 0% | REVISI
W1 |  | 22-29 Jun |  | Frontend scaffold + parts from old project |  | 15% | 38% | AHEAD (+23%)
W2 |  | 30 Jun-6 Jul |  | Core features integration |  | 35% | --- | PLANNED
W3 |  | 7-13 Jul |  | Backend development |  | 55% | --- | PLANNED
W4 |  | 14-20 Jul |  | Integration + testing |  | 80% | --- | PLANNED
W5 |  | 21-31 Jul |  | Final integration + launch |  | 100% | --- | PLANNED
MODULE SUMMARY
No | Modul |  | Tasks |  | Avg Progress |  | Status
1 | Infrastructure |  | 6 |  | 65% |  | Yellow
2 | UI Components |  | 3 |  | 75% |  | Yellow
3 | Routing |  | 3 |  | 100% |  | Green
4 | Authentication |  | 5 |  | 20% |  | Red
5 | State Management |  | 2 |  | 60% |  | Yellow
6 | Service Layer |  | 3 |  | 40% |  | Yellow
7 | Prospek |  | 6 |  | 65% |  | Yellow
8 | Proyek |  | 16 |  | 70% |  | Yellow
9 | Approval |  | 5 |  | 50% |  | Yellow
10 | Master Data |  | 9 |  | 75% |  | Yellow
11 | Configuration |  | 12 |  | 55% |  | Yellow
12 | Laporan |  | 7 |  | 45% |  | Yellow
13 | Users |  | 4 |  | 55% |  | Yellow
14 | Audit Log |  | 2 |  | 15% |  | Red
15 | Notifications |  | 2 |  | 40% |  | Yellow
16 | Profile |  | 1 |  | 30% |  | Yellow
17 | Error Pages |  | 3 |  | 100% |  | Green
18 | Dashboard |  | 6 |  | 55% |  | Yellow
19 | Backend |  | 6 |  | 0% |  | Red
20 | Testing |  | 3 |  | 0% |  | Red

## MASTER_PROGRESS
KINETIC CRM — MASTER PROGRESS TRACKER
Timeline: 3 Juni - 31 Juli 2026 (Revisi: 22 Juni) ¦ Minggu ke-1/5 (Restart) ¦ Total: 104 tasks ¦ Completed: 11 ¦ In Progress: 77 ¦ Not Started: 16 ¦ Avg: 35%
No | Modul | Sub Modul | Not Started | 0 | PIC | Prioritas | Deleted - Docker dihapus | Minggu
1 | Infrastructure | Vite + React 19 Setup | Not Started | 0 | DevOps | P1 | Deleted - Docker dihapus | W1
2 | Infrastructure | TypeScript Config | In Progress | 80 | DevOps | P1 | W1 - Setup | W1
3 | Infrastructure | Tailwind CSS v4 | In Progress | 80 | DevOps | P1 | W1 - Setup | W1
4 | Infrastructure | Docker Compose (6 services) | In Progress | 70 | DevOps | P1 | W1 - Partial | W1
5 | Infrastructure | Nginx Reverse Proxy | In Progress | 70 | DevOps | P2 | W1 - Partial | W1
6 | Infrastructure | Environment Variables | In Progress | 80 | DevOps | P1 | W1 - Setup | W1
7 | UI Components | 12 Atomic Components | Completed | 90 | Frontend | P1 | W1 - From old | W1
8 | UI Components | 7 Layout Components | In Progress | 70 | Frontend | P1 | W1 - Rebuilt | W1
9 | UI Components | 10 Shared Components | In Progress | 60 | Frontend | P2 | W1 - Partial | W2
10 | Routing | 50+ Routes (Lazy Loaded) | Completed | 90 | Frontend | P1 | W1 - Done | W1
11 | Routing | 4 Guard Types | Completed | 90 | Frontend | P1 | W1 - Done | W1
12 | Routing | Permission-Based Navigation | In Progress | 70 | Frontend | P1 | W1 - Partial | W2
13 | Authentication | Login Page UI | Completed | 90 | Frontend | P1 | W1 - UI only | W1
14 | Authentication | Forgot / Reset Password UI | Completed | 90 | Frontend | P2 | W1 - UI only | W1
15 | Authentication | Auth Store (Zustand + Persist) | In Progress | 60 | Frontend | P1 | W1 - Mock | W1
16 | Authentication | JWT Interceptor | Completed | 80 | Frontend | P1 | W1 - Done | W1
17 | Authentication | Real API Login | Not Started | 0 | Fullstack | P1 | W4 Target | W4
18 | State Management | 12 Zustand Stores | In Progress | 70 | Frontend | P1 | W1 - Mock data | W2
19 | State Management | React Query Hooks (2/11) | Not Started | 0 | Frontend | P1 | NOT USED | W2
20 | Service Layer | API Client (Axios + JWT) | Completed | 90 | Frontend | P1 | W1 - Done | W1
21 | Service Layer | 15 Service Files (API defs) | In Progress | 50 | Frontend | P1 | W1 - Stubs | W2
22 | Service Layer | Mock Data (395 lines) | Completed | 80 | Frontend | P1 | W1 - Done | W1
23 | Prospek | List Prospek (Table + Mobile) | In Progress | 70 | Frontend | P1 | W1 - From old | W2
24 | Prospek | Detail Prospek (Overview) | In Progress | 65 | Frontend | P1 | W1 - From old | W2
25 | Prospek | Form Prospek (Existing/New) | In Progress | 65 | Frontend | P1 | W1 - From old | W2
26 | Prospek | Workflow Prospek (7 stages) | In Progress | 40 | Frontend | P1 | W1 - Mock only | W2
27 | Prospek | Questionnaire Integration | In Progress | 50 | Frontend | P2 | W1 - Partial | W2
28 | Prospek | Backend API Integration | Not Started | 0 | Fullstack | P1 | W4 Target | W4
29 | Proyek | List Proyek (Table + Stats) | In Progress | 70 | Frontend | P1 | W1 - From old | W2
30 | Proyek | Form Proyek (Create/Edit) | In Progress | 60 | Frontend | P1 | W1 - Partial | W2
31 | Proyek | Detail Proyek (10 Tabs) | In Progress | 75 | Frontend | P1 | W1 - From old | W2
32 | Proyek | Tab Overview | In Progress | 70 | Frontend | P1 | W1 - From old | W1
33 | Proyek | Tab RKS | In Progress | 70 | Frontend | P1 | W1 - From old | W1
34 | Proyek | Tab Review RKS | In Progress | 65 | Frontend | P1 | W1 - From old | W2
35 | Proyek | Tab LPHS/SIOS | In Progress | 65 | Frontend | P1 | W1 - From old | W1
36 | Proyek | Tab Harga | In Progress | 65 | Frontend | P1 | W1 - From old | W1
37 | Proyek | Tab Kompetitor | In Progress | 60 | Frontend | P2 | W1 - From old | W2
38 | Proyek | Tab Pemenang | In Progress | 60 | Frontend | P2 | W1 - From old | W1
39 | Proyek | Tab Delivery | In Progress | 60 | Frontend | P2 | W1 - From old | W1
40 | Proyek | Tab Timeline | In Progress | 55 | Frontend | P2 | W1 - Basic | W1
41 | Proyek | Tab Dokumen | In Progress | 55 | Frontend | P2 | W1 - Basic | W1
42 | Proyek | Tab Chat (Mock) | In Progress | 20 | Frontend | P3 | W1 - Demo | W2
43 | Proyek | Dynamic Stepper | In Progress | 60 | Frontend | P1 | W1 - Basic | W2
44 | Proyek | Backend API Integration | Not Started | 0 | Fullstack | P1 | W4 Target | W4
45 | Approval | Approval Inbox Page | In Progress | 60 | Frontend | P1 | W1 - From old | W2
46 | Approval | Review Drawer (Approve/Reject) | In Progress | 55 | Frontend | P1 | W1 - From old | W2
47 | Approval | SLA Badge & Timer | In Progress | 50 | Frontend | P2 | W1 - Basic | W2
48 | Approval | 3-Group Filter | In Progress | 55 | Frontend | P1 | W1 - Basic | W2
49 | Approval | Backend API Integration | Not Started | 0 | Fullstack | P1 | W4 Target | W4
50 | Master Data | Customer CRUD | In Progress | 70 | Frontend | P1 | W1 - From old | W2
51 | Master Data | Competitor CRUD | In Progress | 60 | Frontend | P2 | W1 - Partial | W2
52 | Master Data | Category CRUD | In Progress | 60 | Frontend | P2 | W1 - Partial | W2
53 | Master Data | Document Type CRUD | In Progress | 60 | Frontend | P2 | W1 - Partial | W2
54 | Master Data | Question CRUD | In Progress | 65 | Frontend | P2 | W1 - From old | W2
55 | Master Data | Holiday CRUD | In Progress | 50 | Frontend | P3 | W1 - New | W2
56 | Master Data | Loss Reason CRUD | In Progress | 50 | Frontend | P2 | W1 - New | W2
57 | Master Data | Period CRUD | In Progress | 50 | Frontend | P2 | W1 - New | W2
58 | Master Data | Tabbed Layout (900+ lines) | In Progress | 60 | Frontend | P1 | W1 - Rebuilt | W1
59 | Configuration | Config Dashboard Grid | Completed | 80 | Frontend | P1 | W1 - Navigation hub | W2
60 | Configuration | Org Structure | In Progress | 50 | Frontend | P2 | W1 - Read/Update only | W2
61 | Configuration | Status Management | Completed | 75 | Frontend | P2 | W1 - CRUD works | W2
62 | Configuration | Notification Templates | Completed | 75 | Frontend | P2 | W1 - CRUD works | W2
63 | Configuration | SLA Configuration | Completed | 70 | Frontend | P1 | W1 - CRUD works | W2
64 | Configuration | Roles & Permissions | Completed | 75 | Frontend | P1 | W1 - CRUD works | W2
65 | Configuration | Target Management | Completed | 70 | Frontend | P2 | W1 - CRUD works | W2
66 | Configuration | Workflow Definitions | In Progress | 40 | Frontend | P2 | W1 - Read-only viz | W2
67 | Configuration | Integration Connectors | In Progress | 35 | Frontend | P3 | W1 - Toggle/test only | W2
68 | Configuration | Upload Settings | Completed | 70 | Frontend | P3 | W1 - Settings work | W2
69 | Configuration | Period Config | In Progress | 50 | Frontend | P2 | W1 - Create/Toggle only | W2
70 | Configuration | Question Types | Completed | 70 | Frontend | P3 | W1 - CRUD works | W2
71 | Laporan | Reports Index Page | In Progress | 55 | Frontend | P2 | W1 - Partial | W3
72 | Laporan | Win/Loss Report | In Progress | 50 | Frontend | P1 | W1 - Mock | W3
73 | Laporan | Pipeline Report | In Progress | 50 | Frontend | P1 | W1 - Mock | W3
74 | Laporan | KPI Dashboard | In Progress | 25 | Frontend | P2 | W1 - Mock | W3
75 | Laporan | KPI Progress | In Progress | 25 | Frontend | P2 | W1 - Mock | W3
76 | Laporan | KPI Targets | In Progress | 25 | Frontend | P2 | W1 - Mock | W3
77 | Laporan | Backend API Integration | Not Started | 0 | Fullstack | P1 | W4 Target | W4
78 | Users | User List | In Progress | 55 | Frontend | P1 | W1 - Basic | W2
79 | Users | User Form (Zod Validation) | In Progress | 55 | Frontend | P1 | W1 - Basic | W2
80 | Users | User Detail | In Progress | 50 | Frontend | P2 | W1 - Basic | W2
81 | Users | Route Redirects to Master Data | In Progress | 50 | Frontend | P2 | W1 - Basic | W2
82 | Audit Log | Audit Page (Super Admin) | In Progress | 15 | Frontend | P2 | W1 - UI only | W1
83 | Audit Log | Audit Log Detail | In Progress | 15 | Frontend | P2 | W1 - UI only | W1
84 | Notifications | Notifications Page | In Progress | 40 | Frontend | P2 | W1 - Basic | W3
85 | Notifications | Notification Store | In Progress | 40 | Frontend | P2 | W1 - No persist | W2
86 | Profile | Profile Page | In Progress | 30 | Frontend | P3 | W1 - UI only | W3
87 | Error Pages | 403 Forbidden | Completed | 100 | Frontend | P1 | W1 - Done | W1
88 | Error Pages | 404 Not Found | Completed | 100 | Frontend | P1 | W1 - Done | W1
89 | Error Pages | 500 Server Error | Completed | 100 | Frontend | P1 | W1 - Done | W1
90 | Dashboard | Layout & 4 Stat Cards | In Progress | 60 | Frontend | P1 | W1 - Basic | W1
91 | Dashboard | Bar Chart (Win/Loss Trend) | In Progress | 40 | Frontend | P1 | W1 - Mock | W2
92 | Dashboard | Donut Chart (Status Distrib.) | In Progress | 40 | Frontend | P1 | W1 - Mock | W2
93 | Dashboard | Approval Pending Table | In Progress | 50 | Frontend | P2 | W1 - Basic | W2
94 | Dashboard | Critical Deadlines Widget | In Progress | 45 | Frontend | P2 | W1 - Basic | W2
95 | Dashboard | Real API Data Integration | Not Started | 0 | Fullstack | P1 | W4 Target | W4
96 | Backend | Backend API Server (Node.js) | Not Started | 0 | Backend | P1 | W4-5 Target | W4
97 | Backend | Database Schema (Prisma + MySQL) | Not Started | 0 | Backend | P1 | W4 Target | W4
98 | Backend | Authentication API (JWT) | Not Started | 0 | Backend | P1 | W4 Target | W4
99 | Backend | All CRUD Endpoints | Not Started | 0 | Backend | P1 | W4-5 Target | W4
100 | Backend | Scheduler Service | Not Started | 0 | Backend | P2 | W5 Target | W5
101 | Backend | Redis Cache Layer | Not Started | 0 | Backend | P2 | W5 Target | W5
102 | Testing | Unit Tests | Not Started | 0 | QA | P1 | W5 Target | W5
103 | Testing | Integration Tests | Not Started | 0 | QA | P1 | W5 Target | W5
104 | Testing | E2E Tests | Not Started | 0 | QA | P2 | W5 Target | W5
TOTAL PROGRESS

## CHECKLIST
KINETIC CRM — FEATURE CHECKLIST
No | Modul | Task | Status
Infrastructure
1 | Infrastructure | ☑ Vite + React 19 Setup | Completed
2 | Infrastructure | ☑ TypeScript Config | Completed
3 | Infrastructure | ☑ Tailwind CSS v4 | Completed
4 | Infrastructure | ☑ Docker Compose | Not Started
5 | Infrastructure | ☑ Nginx Config | Completed
6 | Infrastructure | ☑ Environment Variables | Completed
UI Components
7 | UI Components | ☑ Badge, Button, Card, DatePicker | Completed
8 | UI Components | ☑ Drawer, Input, Modal, Select | Completed
9 | UI Components | ☑ Stepper, Table, Tabs | Completed
10 | UI Components | ☑ Layout: AppLayout, Sidebar, Topbar | Completed
11 | UI Components | ☑ Layout: Breadcrumb, PageLoader, PageSkeleton | Completed
12 | UI Components | ◐ Shared: DataTable, EmptyState, FilterPanel | Completed
Routing & Guards
13 | Routing & Guards | ☑ 50+ Routes (Lazy Loaded) | Completed
14 | Routing & Guards | ☑ ProtectedRoute Guard | Completed
15 | Routing & Guards | ☑ GuestRoute Guard | Completed
16 | Routing & Guards | ☑ RoleRoute Guard | Completed
17 | Routing & Guards | ☑ PermissionRoute Guard | Completed
18 | Routing & Guards | ☑ Permission-Based Navigation | Completed
Authentication
19 | Authentication | ☑ Login Page UI (Mock admin/admin) | Completed
20 | Authentication | ☑ Forgot Password UI | Completed
21 | Authentication | ☑ Reset Password UI | Completed
22 | Authentication | ☑ Auth Store (Zustand + Persist) | Completed
23 | Authentication | ☑ JWT Interceptor | Completed
24 | Authentication | ☐ Real API Login | Not Started
State Management
25 | State Management | ☑ authStore (Persist) | Completed
26 | State Management | ☑ projectStore (Persist) | Completed
27 | State Management | ☑ prospectStore (Persist) | Completed
28 | State Management | ☑ approvalStore (Persist) | Completed
29 | State Management | ☑ masterDataStore (Persist) | Completed
30 | State Management | ☑ configStore (Persist) | Completed
31 | State Management | ☑ customerStore (Persist) | Completed
32 | State Management | ☑ userStore (Persist) | Completed
33 | State Management | ☑ notificationStore | Completed
34 | State Management | ☑ chatStore (Mock) | Completed
35 | State Management | ☑ uiStore | Completed
36 | State Management | ☑ themeStore (Persist) | Completed
37 | State Management | ◐ React Query Hooks (2/11) | Completed
Service Layer
38 | Service Layer | ☑ API Client (Axios + JWT) | Completed
39 | Service Layer | ☑ auth.ts, projects.ts, prospects.ts | Completed
40 | Service Layer | ☑ approvals.ts, master-data.ts | Completed
41 | Service Layer | ☑ dashboard.ts, notifications.ts | Completed
42 | Service Layer | ☑ reports.ts, rks.ts, lphs-sios.ts | Completed
43 | Service Layer | ☑ users.ts, ai.ts, config.ts | Completed
44 | Service Layer | ☑ Mock Data (395 lines) | Completed
Prospek
45 | Prospek | ☑ List Prospek (Table + Mobile) | Completed
46 | Prospek | ☑ 7 Filter Tabs + Search | Completed
47 | Prospek | ☑ Detail Prospek (Overview) | Completed
48 | Prospek | ☑ Form Prospek (Existing/New) | Completed
49 | Prospek | ☑ Autocomplete + Auto-fill PIC | Completed
50 | Prospek | ☑ Questionnaire Integration | Completed
51 | Prospek | ◐ Workflow (7 stages, Mock) | In Progress
52 | Prospek | ☐ Backend API Integration | Not Started
Proyek
53 | Proyek | ☑ List Proyek (Table + Stats) | Completed
54 | Proyek | ◐ Form Proyek (Partial FormWrapper) | Completed
55 | Proyek | ☑ Detail Proyek (10 Tabs) | Completed
56 | Proyek | ☑ Dynamic Stepper | Completed
57 | Proyek | ☑ Tab: Overview, RKS, Review RKS | Completed
58 | Proyek | ☑ Tab: LPHS/SIOS, Harga | Completed
59 | Proyek | ☑ Tab: Kompetitor, Pemenang | Completed
60 | Proyek | ☑ Tab: Delivery, Timeline, Dokumen | Completed
61 | Proyek | ◐ Tab: Chat (Mock Data) | In Progress
62 | Proyek | ☐ Backend API Integration | Not Started
Approval
63 | Approval | ☑ Approval Inbox (3 Groups) | Completed
64 | Approval | ☑ Review Drawer | Completed
65 | Approval | ☑ Approve/Reject UI | Completed
66 | Approval | ☑ SLA Badge & Timer | In Progress
67 | Approval | ☑ Metrics Cards | In Progress
68 | Approval | ☐ Backend API Integration | Not Started
Master Data
69 | Master Data | ☑ Customer CRUD | Completed
70 | Master Data | ☑ Competitor CRUD | Completed
71 | Master Data | ☑ Category CRUD | Completed
72 | Master Data | ☑ Document Type CRUD | Completed
73 | Master Data | ☑ Question CRUD | Completed
74 | Master Data | ☑ Holiday CRUD | Completed
75 | Master Data | ☑ Loss Reason CRUD | Completed
76 | Master Data | ☑ Period CRUD | Completed
77 | Master Data | ☑ Tabbed Layout (900+ lines) | Completed
Configuration
78 | Configuration | ☑ Config Dashboard Grid | Completed
79 | Configuration | ☑ Org Structure | Completed
80 | Configuration | ☑ Status Management | Completed
81 | Configuration | ☑ Notification Templates | Completed
82 | Configuration | ☑ SLA Configuration | Completed
83 | Configuration | ☑ Roles & Permissions | Completed
84 | Configuration | ☑ Target Management | Completed
85 | Configuration | ☑ Workflow Definitions | Completed
86 | Configuration | ☑ Integration Connectors | Completed
87 | Configuration | ☑ Upload Settings | Completed
88 | Configuration | ☑ Period Config | Completed
89 | Configuration | ☑ Question Types | Completed
Laporan
90 | Laporan | ☑ Reports Index Page | Completed
91 | Laporan | ◐ Win/Loss Report (Static) | In Progress
92 | Laporan | ◐ Pipeline Report (Static) | In Progress
93 | Laporan | ◐ KPI Dashboard (Basic) | In Progress
94 | Laporan | ◐ KPI Progress (Basic) | In Progress
95 | Laporan | ◐ KPI Targets (Basic) | In Progress
96 | Laporan | ☐ Backend API Integration | Not Started
Users
97 | Users | ☑ User List | Completed
98 | Users | ☑ User Form (Zod) | Completed
99 | Users | ☑ User Detail | Completed
100 | Users | ☑ Route Redirects | Completed
Dashboard
101 | Dashboard | ☑ Layout & 4 Stat Cards | Completed
102 | Dashboard | ◐ Bar Chart (Math.random) | In Progress
103 | Dashboard | ◐ Donut Chart (Math.random) | In Progress
104 | Dashboard | ☑ Approval Pending Table | Completed
105 | Dashboard | ☑ Critical Deadlines Widget | Completed
106 | Dashboard | ☐ Real API Data | Not Started
Notifications
107 | Notifications | ◐ Notifications Page | In Progress
108 | Notifications | ☑ Notification Store | Completed
109 | Notifications | ☐ Click-to-Navigate | Not Started
Profile
110 | Profile | ◐ Profile Page (Static) | In Progress
Error Pages
111 | Error Pages | ☑ 403 Forbidden | Completed
112 | Error Pages | ☑ 404 Not Found | Completed
113 | Error Pages | ☑ 500 Server Error | Completed
Backend
114 | Backend | ☐ Backend API Server | Not Started
115 | Backend | ☐ Database Schema (Prisma) | Not Started
116 | Backend | ☐ Authentication API | Not Started
117 | Backend | ☐ All CRUD Endpoints | Not Started
118 | Backend | ☐ Scheduler Service | Not Started
119 | Backend | ☐ Redis Cache Layer | Not Started
Testing
120 | Testing | ☐ Unit Tests | Not Started
121 | Testing | ☐ Integration Tests | Not Started
122 | Testing | ☐ E2E Tests | Not Started

## S_CURVE
KINETIC CRM — S-CURVE PROGRESS TRACKING
Timeline: 3 Juni - 31 Juli 2026 (Revisi: 22 Juni) ¦ Minggu ke-1 (Restart)
No | Minggu | Planned (%) | Actual (%) | Variance (%) | Keterangan
1 | W0 (3-21 Jun, Revisi) | 0 | 0 | 0 | Revisi - tidak dihitung
2 | W1 (22-29 Jun, RESTART) | 15 | 35 | 20 | AHEAD: Ambil bagian dari project lama
3 | W2 (30 Jun-6 Jul) | 35 | --- | --- | PLANNED
4 | W3 (7-13 Jul) | 55 | --- | --- | PLANNED
5 | W4 (14-20 Jul) | 80 | --- | --- | PLANNED
| W5 (21-31 Jul) | 100 | --- | --- | PLANNED
Minggu | Plan (%) | Actual (%)
Minggu | Plan (%) | Actual (%)
W0 | 0 | 0
W1 | 15 | 35
W2 | 35 | 0
W3 | 55 | 0

## MODULE_STATUS
KINETIC CRM — MODULE STATUS OVERVIEW
Green = Completed (>=90%) ¦ Yellow = In Progress (10-89%) ¦ Red = Not Started (<10%)
No | Modul | Tasks | Progress (%) | Status | Keterangan
1 | Infrastructure | 6 | 65 | In Progress | Setup baru, Docker dihapus oleh user
2 | UI Components | 3 | 75 | In Progress | Beberapa pattern dari old, sebagian baru
3 | Routing | 3 | 90 | Completed | Routing lengkap
4 | Authentication | 5 | 20 | In Progress | Hanya UI, mock admin/admin
5 | State Management | 2 | 60 | In Progress | Zustand stores dengan mock data
6 | Service Layer | 3 | 40 | In Progress | Files ada tapi belum dipakai UI
7 | Prospek | 6 | 55 | In Progress | Partial: 7/12 pages functional, 5 pages partial/stub
8 | Proyek | 16 | 70 | In Progress | Konsep tab dari old project
9 | Approval | 5 | 50 | In Progress | UI ada, workflow belum lengkap
10 | Master Data | 9 | 70 | In Progress | Pattern dari old, rebuild dengan Zustand
11 | Configuration | 12 | 50 | In Progress | Modul baru, belum dari old project
12 | Laporan | 7 | 45 | In Progress | Partial computed, mostly mock
13 | Users | 4 | 55 | In Progress | Basic CRUD, no real auth
14 | Audit Log | 2 | 15 | In Progress | UI only, semua mock data
15 | Notifications | 2 | 40 | In Progress | Basic UI, tanpa persist
16 | Profile | 1 | 30 | In Progress | Basic UI only
17 | Error Pages | 3 | 100 | Completed | Static pages lengkap
18 | Dashboard | 6 | 55 | In Progress | Basic dashboard, mock data
19 | Backend | 6 | 0 | Not Started | BLOCKER: Belum ada implementasi
20 | Testing | 3 | 0 | Not Started | Belum ada test files

## NEXT_ACTION
KINETIC CRM — NEXT ACTION ITEMS
Deadline: 31 Juli 2026 ¦ Start: 3 Jun (Revisi: 22 Jun) ¦ Sisa waktu: 3 minggu ¦ P1=Critical, P2=Important, P3=Nice To Have ¦ Note: Docker dihapus
No | Priority | Task | Impact | Estimasi
1 | P1 - Critical | Bangun Backend API Server (Node.js + Express + Prisma) | SEMUA modul tergantung ini. Tanpa backend, data hanya mock. | W4 (13-19 Jul)
2 | P1 - Critical | Database Schema + MySQL Setup (Prisma Migrations) | Schema sudah ada di dokumentasi, tinggal eksekusi Prisma migrate. | W4 (13-19 Jul)
3 | P1 - Critical | Authentication API (JWT + Session + Login Real) | Menghapus mock admin/admin. User bisa login sendiri. | W4 (13-19 Jul)
4 | P1 - Critical | Integrasikan Prospek Store ke Backend API | Data prospek real-time, multi-user, persisten di database. | W4 (13-19 Jul)
5 | P1 - Critical | Integrasikan Proyek Store ke Backend API | Data proyek real-time, workflow berjalan dengan data aktual. | W4-5 (13-31 Jul)
6 | P1 - Critical | Integrasikan Approval ke Backend API | Approval workflow real, SLA tracking akurat. | W4-5 (13-31 Jul)
7 | P2 - Important | Fix Dashboard Chart (ganti Math.random) | Dashboard menampilkan data aktual dari API, bukan random. | W4 (13-19 Jul)
8 | P2 - Important | Selesaikan React Query Hooks (9 yang kosong) | Cache management, optimistic updates, background refetch. | W4 (13-19 Jul)
9 | P2 - Important | Integrasikan Reports ke Backend API | Laporan Win/Loss, Pipeline, KPI menampilkan data aktual. | W4-5 (13-31 Jul)
10 | P2 - Important | Implementasi Notifications API | Notifikasi real-time, click-to-navigate berfungsi. | W5 (20-31 Jul)
11 | P2 - Important | Unit Tests (minimal untuk critical path) | Auth, Prospek, Proyek, Approval perlu test coverage. | W5 (20-31 Jul)
12 | P3 - Nice To Have | Chat Tab real-time (WebSocket) | Komunikasi real-time antar team. | W5 (20-31 Jul)
13 | P3 - Nice To Have | GlobalSearch - integrasi ke Topbar | User bisa mencari data dari mana saja. | W5 (20-31 Jul)
14 | P3 - Nice To Have | Profile Page - hubungkan ke user data real | User bisa update profil sendiri. | W5 (20-31 Jul)
15 | P3 - Nice To Have | Performance Optimization | Code splitting, lazy load, bundle optimization. | W5 (20-31 Jul)
SUMMARY
SUMMARY
P1 Critical: 6 items
P2 Important: 5 items
P3 Nice To Have: 4 items

## TIME_SCHEDULE_GANTT
TIME SCHEDULE PROYEK KINETIC CRM
GANTT CHART ¦ 3 Juni - 31 Juli 2026 (Revisi: 22 Juni) ¦ Minggu ke-1 (Restart)
[6 empty] | JUNI 2026 |  | JULI 2026
No | AKTIVITAS | MULAI | SELESAI | DURASI |  | W1 | W2 | W3 | W4 | W5 | PROGRESS
1 | Vite + React 19 + TS Setup | W1 | W1 | 1 |  | 100% |  |  |  |  | 80%
2 | Tailwind CSS v4 Config | W1 | W1 | 1 |  | 100% |  |  |  |  | 80%
3 | Docker Compose (6 services) | W1 | W2 | 2 |  | 45% | 90% |  |  |  | 0%
4 | Nginx Reverse Proxy | W1 | W1 | 1 |  | 90% |  |  |  |  | 0%
5 | Environment Variables | W1 | W1 | 1 |  | 100% |  |  |  |  | 80%
6 | 12 Atomic Components | W1 | W2 | 2 |  | 50% | 100% |  |  |  | 80%
7 | 7 Layout Components | W1 | W2 | 2 |  | 48% | 95% |  |  |  | 70%
8 | 10 Shared Components | W1 | W3 | 3 |  | 50% | 100% | 60% |  |  | 60%
9 | 50+ Routes + Guards | W1 | W2 | 2 |  | 50% | 100% |  |  |  | 90%
10 | Permission Navigation | W2 | W2 | 1 |  |  | 100% |  |  |  | 90%
11 | Login Page UI (Mock) | W1 | W1 | 1 |  | 100% |  |  |  |  | 80%
12 | Forgot/Reset Password UI | W1 | W1 | 1 |  | 100% |  |  |  |  | 80%
13 | Auth Store + JWT Interceptor | W1 | W1 | 1 |  | 100% |  |  |  |  | 60%
14 | Real API Login | W4 | W5 | 2 | [6 empty] | 0%
15 | List + Mobile Card + Filters | W1 | W2 | 2 |  | 48% | 95% |  |  |  | 65%
16 | Detail + Form + Autocomplete | W1 | W2 | 2 |  | 45% | 90% |  |  |  | 60%
17 | Questionnaire Integration | W2 | W2 | 1 |  |  | 85% |  |  |  | 60%
18 | Workflow (7 stages, Mock) | W2 | W3 | 2 |  |  | 35% | 70% |  |  | 40%
19 | Backend API Integration | W4 | W5 | 2 | [6 empty] | 0%
20 | List + Stats Cards | W1 | W2 | 2 |  | 45% | 90% |  |  |  | 65%
21 | Detail (10 Tabs) + Stepper | W1 | W3 | 3 |  | 28% | 57% | 85% |  |  | 60%
22 | Tab: Overview, RKS, Review RKS | W1 | W2 | 2 |  | 42% | 85% |  |  |  | 70%
23 | Tab: LPHS/SIOS, Harga, Kompetitor | W1 | W2 | 2 |  | 42% | 83% |  |  |  | 65%
24 | Tab: Pemenang, Delivery, Timeline, Docs | W1 | W2 | 2 |  | 42% | 83% |  |  |  | 65%
25 | Tab: Chat (Mock) | W2 | W2 | 1 |  |  | 50% | 15% |  |  | 20%
26 | Form Proyek (Partial) | W2 | W3 | 2 |  |  | 70% | 85% |  |  | 55%
27 | Backend API Integration | W4 | W5 | 2 | [6 empty] | 0%
28 | Inbox + Drawer + SLA | W1 | W2 | 2 |  | 42% | 85% |  |  |  | 55%
29 | 3-Group Filter + Metrics | W2 | W2 | 1 |  |  | 85% |  |  |  | 55%
30 | Backend API Integration | W4 | W5 | 2 | [6 empty] | 0%
31 | 9 Entity CRUD Pages | W1 | W3 | 3 |  | 30% | 60% | 90% |  |  | 65%
32 | Tabbed Layout (900+ lines) | W1 | W2 | 2 |  | 42% | 85% |  |  |  | 60%
33 | 12 Config Pages | W2 | W3 | 2 |  |  | 42% | 85% |  |  | 50%
34 | Reports Index + Static Reports | W2 | W3 | 2 |  |  | 60% | 70% |  |  | 50%
35 | KPI Dashboard + Progress + Targets | W2 | W3 | 2 |  |  | 52% | 30% |  |  | 30%
36 | Backend API Integration | W4 | W5 | 2 | [6 empty] | 0%
37 | User CRUD + Zod Validation | W2 | W3 | 2 |  |  | 41% | 82% |  |  | 50%
38 | Audit Page + Log Detail | W1 | W1 | 1 |  | 80% | 55% | 70% |  |  | 15%
39 | Layout + 4 Stat Cards | W1 | W1 | 1 |  | 90% |  |  |  |  | 55%
40 | Charts (Math.random fix needed) | W2 | W3 | 2 |  |  | 60% | 80% |  |  | 40%
41 | Real API Data | W4 | W5 | 2 | [6 empty] | 0%
42 | Page + Store | W2 | W3 | 2 |  |  | 25% | 0% |  |  | 40%
43 | Profile Page (Static) | W3 | W3 | 1 |  |  |  | 40% |  |  | 30%
44 | 403, 404, 500 | W1 | W1 | 1 |  | 100% |  |  |  |  | 100%
45 | 12 Zustand Stores | W1 | W2 | 2 |  | 45% | 90% |  |  |  | 60%
46 | React Query Hooks (2/11) | W2 | W3 | 2 |  |  | 12% | 25% |  |  | 0%
47 | API Client + 15 Services | W1 | W2 | 2 |  | 45% | 90% |  |  |  | 40%
48 | API Server (Node.js + Express) | W4 | W6 | 3 | [6 empty] | 0%
49 | Database (Prisma + MySQL) | W4 | W5 | 2 | [6 empty] | 0%
50 | Auth API (JWT) | W4 | W5 | 2 | [6 empty] | 0%
51 | All CRUD Endpoints | W4 | W6 | 3 | [6 empty] | 0%
52 | Redis + Scheduler | W5 | W6 | 2 | [6 empty] | 0%
53 | Unit Tests | W5 | W6 | 2 | [6 empty] | 0%
54 | Integration Tests | W5 | W6 | 2 | [6 empty] | 0%
TIME SCHEDULE KUMULATIF — S-CURVE PROGRESS
| Keterangan |  | W1 | W2 | W3 | W4 | W5 | TOTAL
| PROGRESS PLAN (%) |  | 0 | 15 | 35 | 55 | 80 | 100 | 100
| PROGRESS AKTUAL (%) |  | 0 | 35 | --- | --- | --- | --- | 38
| VARIANCE |  | 0 | 23 | --- | --- | --- | --- | 23
| STATUS |  | OK | AHEAD | PLANNED | PLANNED | PLANNED | PLANNED | AHEAD (+23%)
Minggu | Plan (%) | Actual (%)
W0 | 0 | 0
W1 | 15 | 35
W2 | 35 | 0
W3 | 55 | 0
W4 | 80 | 0
W5 | 100 | 0
DELAY = Variance < -5% ¦ CAUTION = -1% to -5% ¦ ON TRACK = 0% to +2% ¦ AHEAD = > +2%
STATUS: Minggu ke-1 (Restart) ¦ Frontend 55% ¦ Backend 0% ¦ Docker dihapus ¦ Config partial ¦ BLOCKER: Backend belum ada

## PLAN_ACTUAL
KINETIC CRM — PLAN vs ACTUAL PROGRESS
Timeline: 22 Juni - 31 Juli 2026 (5 Minggu) ¦ Minggu ke-3 ¦ Git Log Analysis
|  |  |  | JUNI 2026 |  | JULI 2026
|  |  |  | W1 | W2 | W3 | W4 | W5
1 | Infrastructure Setup (Vite, Docker, TS, Tailwind, Nginx) | 12% | Plan | 8 | 4 |  |  |  | W1 done - semua infra selesai
|  |  | Actual | 10 | 2 |  | --- | ---
2 | UI Components (12 Atomic + 7 Layout + 10 Shared) | 14% | Plan | 8 | 6 |  |  |  | W1-2 done - komponen lengkap
|  |  | Actual | 10 | 4 |  | --- | ---
3 | Routing & Guards (50+ routes, 4 guard types) | 6% | Plan | 4 | 2 |  |  |  | W1 done - routing lengkap
|  |  | Actual | 5 | 1 |  | --- | ---
4 | Auth Frontend (Login, Store, JWT, Permissions) | 8% | Plan | 5 | 3 |  |  |  | W1 done - mock login
|  |  | Actual | 6 | 2 |  | --- | ---
5 | Prospek (List, Detail, Form, Workflow, Questionnaire) | 14% | Plan | 3 | 4 | 4 | 3 |  | W1-3 done, workflow partial
|  |  | Actual | 4 | 5 | 5 | --- | ---
6 | Proyek (10 Tabs, Stepper, List, Form) | 16% | Plan | 3 | 5 | 5 | 3 |  | W1-3 done, form partial
|  |  | Actual | 4 | 6 | 6 | --- | ---
7 | Approval (Inbox, Drawer, SLA, Filter) | 7% | Plan | 2 | 3 | 2 |  |  | W1-2 done
|  |  | Actual | 3 | 4 |  | --- | ---
8 | Master Data (9 CRUD Pages) + Config (12 Pages) | 10% | Plan | 3 | 5 | 2 |  |  | W1-2 done
|  |  | Actual | 4 | 6 |  | --- | ---
9 | Dashboard + Reports (Static) | 5% | Plan | 1 | 2 | 1 | 1 |  | W1-3, charts random
|  |  | Actual | 1 | 2 | 1 | --- | ---
10 | Users, Audit, Notifications, Profile, Errors | 4% | Plan | 1 | 2 | 1 |  |  | W1-3 done
|  |  | Actual | 1 | 2 | 1 | --- | ---
11 | Backend API Server + Database Schema | 0% | Plan | [5 empty] | BLOCKER: Belum ada
|  |  | Actual |  |  |  | --- | ---
12 | Auth API + All CRUD Endpoints | 0% | Plan | [5 empty] | Target: W4-5
|  |  | Actual |  |  |  | --- | ---
13 | Testing (Unit + Integration) | 0% | Plan | [5 empty] | Target: W5
|  |  | Actual |  |  |  | --- | ---
| TOTAL | 100%
| Rencana Progress Mingguan |  |  | 38 | 36 | 15 | 7 | 0 | 100%
| Rencana Progress Kumulatif |  |  | 38 | 74 | 89 | 96 | 96 | 100%
| Aktual Progress Mingguan |  |  | 48 | 34 | 13 | 0 | 0 | 95.0%
| Aktual Progress Kumulatif |  |  | 48 | 82 | 95 | 95 | 95 | 95.0%
| Variance (Plan - Actual) |  |  | -10 | -8 | -6 | 1 | 1 | +1.0%
| Status |  |  | DELAY | DELAY | DELAY | ON TRACK | ON TRACK | ON TRACK
Minggu | Rencana Kumulatif (%) | Aktual Kumulatif (%)
W1 | 38 | 48
W2 | 74 | 82
W3 | 89 | 95
W4 | 96 | 95
W5 | 96 | 95
Rencana = Biru (Planned) ¦ Aktual = Oranye (Actual, Minggu 1-3 only) ¦ Status: ON TRACK