## DOCUMENT_CATALOG
KINETIC CRM — DOCUMENTATION CATALOG
65 File Dokumentasi Lengkap ¦ Generated from MD Files
No | File | Category | Module Name | Description | Gap Resolution | Status
Overview & Governance
000 | 000_DOCUMENT_INDEX.md | Overview & Governance | Document Index | Daftar seluruh 65 file dokumentasi KINETIC CRM | - | Index
001 | 001_SYSTEM_OVERVIEW.md | Overview & Governance | System Overview | Visi produk, problem statement, business goals & KPI, ruang lingkup in/out scope | - | Final
002 | 002_GLOSSARY_AND_TERMINOLOGY.md | Overview & Governance | Glossary & Terminology | Kamus istilah domain (RKS, LPHS, SIOS, SPK, dll) | - | Final
003 | 003_GAP_TRACEABILITY_MATRIX.md | Overview & Governance | Gap Traceability Matrix | Pemetaan 22 gap BA Review ke dokumen/modul resolusi | 22 gaps resolved | Final
004 | 004_USER_PERSONAS_AND_JOURNEYS.md | Overview & Governance | User Personas & Journeys | 5 persona detail + user journey Prospek-Proyek dan Tender | - | Final
Architecture
005 | 005_SYSTEM_ARCHITECTURE_OVERVIEW.md | Architecture | System Architecture Overview | Arsitektur high-level: FE SPA, BE REST API, DB, container, AI service layer | - | Final
006 | 006_TECH_STACK_SPECIFICATION.md | Architecture | Tech Stack Specification | Stack lengkap FE (React/TS/Tailwind/Zustand/RQ) dan BE/DB | - | Final
007 | 007_DATA_ARCHITECTURE_PRINCIPLES.md | Architecture | Data Architecture Principles | Prinsip normalisasi, versioning, soft-delete, audit-by-design, optimistic locking | - | Final
008 | 008_SECURITY_ARCHITECTURE.md | Architecture | Security Architecture | Auth JWT, RBAC, encryption, OWASP controls, secrets management | - | Final
009 | 009_INTEGRATION_ARCHITECTURE.md | Architecture | Integration Architecture | Integrasi fase 2/3: SMTP, SSO/SAML, WhatsApp/Teams, ERP/CRM API | - | Final
010 | 010_AI_INTEGRATION_ARCHITECTURE.md | Architecture | AI Integration Architecture | AI Service Layer, Provider Abstraction, Gemini API Integration | - | Final
011 | 011_AI_FEATURES_AND_USE_CASES.md | Architecture | AI Features & Use Cases | Katalog fitur AI: Tender Summary, RKS Summary, Prospect Analysis, dll | - | Final
012 | 012_INFORMATION_ARCHITECTURE_AND_NAVIGATION.md | Architecture | Information Architecture & Navigation | Sitemap, struktur menu, sidebar navigation, breadcrumb rules | - | Final
Reference & Catalog
013 | 013_GLOBAL_STATE_MACHINE_REFERENCE.md | Reference & Catalog | Global State Machine Reference | Referensi pusat seluruh lifecycle status lintas modul | - | Final
014 | 014_UI_SCREEN_CATALOG.md | Reference & Catalog | UI Screen Catalog | Katalog seluruh layar sistem dengan Purpose, Roles, Components | - | Final
Organization & Access
015 | 015_ORGANIZATION_HIERARCHY_MODULE.md | Organization & Access | Organization Hierarchy | Modul Company-Division-Department-Branch penuh | GAP-05 | Final
016 | 016_POSITION_MANAGEMENT_MODULE.md | Organization & Access | Position Management | Master Position/Job Title untuk approval berbasis posisi | CFG-04 | Final
017 | 017_ROLE_PERMISSION_MODULE.md | Organization & Access | Role & Permission | Modul Role & Permission dinamis, permission matrix | CFG-04 | Final
018 | 018_USER_MANAGEMENT_MODULE.md | Organization & Access | User Management | CRUD user, reset password, lock/unlock, assignment | - | Final
019 | 019_AUTHENTICATION_SESSION_MODULE.md | Organization & Access | Authentication & Session | Login, session lifecycle, idle timeout, lockout | FR001-FR004 | Final
020 | 020_AUTHORIZATION_ENFORCEMENT_SPEC.md | Organization & Access | Authorization Enforcement | Spek teknis enforcement RBAC di setiap layer | - | Final
Master Data
021 | 021_MASTER_CUSTOMER_AND_CATEGORY.md | Master Data | Master Customer & Category | Master Customer, Kategori Proyek, Industri | MD04, CFG-11 | Final
022 | 022_MASTER_PROJECT_STATUS_AND_DOCUMENT_TYPE.md | Master Data | Master Status & Document Type | Master Status Proyek dinamis, Master Tipe Dokumen | MD05, MD11 | Final
023 | 023_MASTER_COMPETITOR_MODULE.md | Master Data | Master Competitor | Normalisasi Master Kompetitor, relasi many-to-many ke proyek | GAP-09, MD14 | Final
024 | 024_MASTER_QUESTION_AND_QUESTION_TYPE.md | Master Data | Master Question & Type | Master Pertanyaan plus migrasi Question Type dari localStorage | GAP-03, FR102, CFG-12 | Final
025 | 025_MASTER_PERIOD_AND_HOLIDAY_CALENDAR.md | Master Data | Master Period & Holiday | Master Periode Pelaporan, Master Hari Libur untuk SLA | MD10, MD13 | Final
026 | 026_MASTER_LOSS_REASON_AND_MISC.md | Master Data | Master Loss Reason | Master Alasan Kekalahan, master pendukung lain | GAP-12 | Final
Configuration
027 | 027_CONFIG_ORGANIZATION_AND_WORKFLOW.md | Configuration | Config Organization & Workflow | CFG-01 (Org) dan CFG-02 (Approval Workflow) | CFG-01, CFG-02 | Final
028 | 028_CONFIG_STATUS_CATEGORY_ROLE.md | Configuration | Config Status, Category, Role | CFG-03 (Status Proyek), CFG-04 (Role), CFG-11 (Kategori) | CFG-03, CFG-04, CFG-11 | Final
029 | 029_CONFIG_SLA_REMINDER_ESCALATION.md | Configuration | Config SLA & Escalation | CFG-05 (SLA) dan CFG-06 (Reminder/Eskalasi) | CFG-05, CFG-06 | Final
030 | 030_CONFIG_TARGET_DASHBOARD_NOTIFICATION.md | Configuration | Config Target, Dashboard, Notif | CFG-07 (Target & Bobot), CFG-08 (Dashboard), CFG-09 (Notifikasi) | CFG-07, CFG-08, CFG-09 | Final
031 | 031_CONFIG_SYSTEM_PERIOD_UPLOAD_INTEGRATION.md | Configuration | Config System, Upload, Integration | CFG-10, CFG-12, CFG-13, CFG-14 (termasuk AI provider) | CFG-10, CFG-12, CFG-13, CFG-14 | Final
Core Modules
032 | 032_PROSPECT_MANAGEMENT_MODULE.md | Core Modules | Prospect Management | CRUD Prospek, state lifecycle, approval PM, revisi, konversi | FR010-FR015 | Final
033 | 033_PROJECT_CORE_MODULE.md | Core Modules | Project Core | Entitas Project inti, dua tipe (tender/prospecting), state machine | GAP-04, CFG-03 | Final
034 | 034_RKS_MODULE.md | Core Modules | RKS Module | Input data tender, upload dokumen, checklist pertanyaan, review PM | FR030-FR033 | Final
035 | 035_LPHS_SIOS_MODULE.md | Core Modules | LPHS/SIOS Module | Draft upload, approval multi-departemen paralel, revisi tertarget | GAP-08, BP-02, BP-03 | Final
036 | 036_HARGA_KOMPETITOR_MODULE.md | Core Modules | Harga & Kompetitor | Input penawaran harga, data kompetitor per proyek | FR050-FR051 | Final
037 | 037_PEMENANG_DELIVERY_MODULE.md | Core Modules | Pemenang & Delivery | Pencatatan hasil tender (menang/kalah + loss reason) & delivery | FR060-FR062 | Final
038 | 038_PROJECT_CANCELLATION_MODULE.md | Core Modules | Project Cancellation | Status cancelled penuh: business rule, hak akses, dampak laporan | GAP-04, BP-04 | Final
Workflow Engine
039 | 039_APPROVAL_ENGINE_CORE.md | Workflow Engine | Approval Engine Core | Engine approval generik: stage, decision, precondition, audit trail | GAP-06, GAP-07, GAP-08 | Final
040 | 040_PARALLEL_REVIEW_AND_TARGETED_REVISION.md | Workflow Engine | Parallel Review & Revision | Redesain paralelisasi review Dept+PM & revisi LPHS tertarget | GAP-08, BP-02, BP-03 | Final
041 | 041_SLA_ESCALATION_ENGINE.md | Workflow Engine | SLA & Escalation Engine | Kalkulasi hari kerja, reminder T-X, eskalasi otomatis | GAP-06, BP-01 | Final
042 | 042_BACKUP_APPROVER_AND_REASSIGNMENT.md | Workflow Engine | Backup Approver & Reassignment | Backup approver & re-assign manual oleh admin | GAP-07 | Final
Target & KPI
043 | 043_TARGET_KPI_DATA_MODEL_AND_BUSINESS_RULES.md | Target & KPI | Target & KPI Data Model | Master KPI, Master Target (versioned), Master Bobot, formula skor | GAP-01 Critical | Final
044 | 044_TARGET_SETTING_WORKFLOW.md | Target & KPI | Target Setting Workflow | Workflow input/update target oleh admin/management, histori versi | GAP-01, CFG-07 | Final
045 | 045_PROGRESS_MONITORING_AND_SCORING.md | Target & KPI | Progress Monitoring & Scoring | Kalkulasi progress real-time vs target, snapshot, traffic-light | GAP-01 | Final
Notification
046 | 046_INAPP_NOTIFICATION_MODULE.md | Notification | In-App Notification | Notifikasi in-app: polling, tipe event, trigger matrix, badge | GAP-13, FR090-FR091 | Final
047 | 047_EMAIL_AND_EXTERNAL_NOTIFICATION_FASE2.md | Notification | Email & External Notification | Desain notifikasi email/WhatsApp/Teams & approval one-click (Fase 2/3) | GAP-18, GAP-19 | Final
Document Management
048 | 048_DOCUMENT_UPLOAD_STORAGE_MODULE.md | Document Management | Document Upload & Storage | Upload, validasi tipe/ukuran, storage di luar webroot | FR070-FR071 | Final
049 | 049_DOCUMENT_VERSIONING_MODULE.md | Document Management | Document Versioning | Versioning dokumen: model data, UI histori versi, business rules | GAP-14 | Final
Dashboard
050 | 050_DASHBOARD_MODULE.md | Dashboard | Dashboard Module | Dashboard per role + filter granular, widget, AI Executive Summary | GAP-10, D.6 | Final
Reporting
051 | 051_REPORTING_MODULE.md | Reporting | Reporting Module | Laporan Win/Loss, Pipeline, Progress vs Target, export Excel/PDF | GAP-11 | Final
Audit
052 | 052_AUDIT_TRAIL_MODULE.md | Audit | Audit Trail Module | Audit log append-only, payload before/after, export CSV | GAP-16 | Final
Database
053 | 053_FULL_ENTITY_RELATIONSHIP_DIAGRAM.md | Database | Entity Relationship Diagram | ERD lengkap seluruh entitas (40+ tabel), relasi, kardinalitas | - | Final
054 | 054_FULL_DATABASE_SCHEMA_DDL.md | Database | Database Schema DDL | DDL lengkap: semua tabel, kolom, tipe data, constraint, FK | - | Final
055 | 055_INDEXING_AND_QUERY_OPTIMIZATION_STRATEGY.md | Database | Indexing & Query Optimization | Strategi index per tabel, query pattern kritis | - | Final
API
056 | 056_API_CONVENTIONS_AND_STANDARDS.md | API | API Conventions & Standards | Konvensi REST, versioning, format response/error, pagination | - | Final
057 | 057_FULL_API_ENDPOINT_SPECIFICATION.md | API | Full API Endpoint Spec | Spesifikasi lengkap seluruh endpoint per modul termasuk AI | - | Final
Frontend
058 | 058_FRONTEND_ARCHITECTURE_AND_COMPONENT_LIBRARY.md | Frontend | Frontend Architecture | Struktur folder, konvensi kode, state management, UI component library | - | Final
Non-Functional
059 | 059_NON_FUNCTIONAL_REQUIREMENTS.md | Non-Functional | Non-Functional Requirements | Security, performance, scalability, reliability, accessibility | - | Final
Infrastructure
060 | 060_DOCKER_DEPLOYMENT_AND_OPERATIONS.md | Infrastructure | Docker Deployment & Ops | Docker Compose, Dockerfile, health check, secret management, backup | GAP-15 | Final
061 | 061_DATA_MIGRATION_STRATEGY.md | Infrastructure | Data Migration Strategy | Migrasi data manual/spreadsheet ke KINETIC CRM | GAP-03 (localStorage) | Final
QA & Testing
062 | 062_MASTER_TEST_CASE_CATALOG.md | QA & Testing | Master Test Case Catalog | Seluruh test case per modul (positif/negatif/edge/security) | - | Final

## BUSINESS_GOALS
KINETIC CRM — BUSINESS GOALS & KPI
8 Business Goals (6 PRD + 2 Inferred) ¦ From Doc 001
ID | Business Goal | Success Indicator (KPI) | Target | Supporting Module
BG-01 | Digitalisasi end-to-end alur prospek dan tender | Eliminasi proses manual berbasis email/spreadsheet untuk approval | 100% dalam 3 bulan pasca go-live | Modul Prospek, Project Core, RKS, LPHS/SIOS, Approval Engine
BG-02 | Meningkatkan kecepatan proses approval | Rata-rata waktu per siklus approval < 2 hari kerja | < 2 hari kerja | Approval Engine, SLA & Escalation Engine, Parallel Review
BG-03 | Meningkatkan visibilitas status proyek | % proyek yang status real-time-nya tersedia di dashboard | 100% | Dashboard Module, Project Core
BG-04 | Meningkatkan akurasi pelaporan win/loss | Ketersediaan laporan win rate bulanan otomatis | Tersedia T+1 hari | Reporting Module, Pemenang & Delivery Module
BG-05 | Memastikan compliance dokumen dan audit trail | % approval yang memiliki histori lengkap | 100% | Audit Trail Module, Approval Engine, Document Management
BG-06 | Skalabilitas sistem untuk pertumbuhan volume | Sistem mampu menangani 10x volume tanpa degradasi performa | Tanpa degradasi performa | Architecture, Database Indexing, Infrastructure
BG-07 | Basis objektif evaluasi performa unit organisasi | Tersedianya skor performa komposit per cabang/divisi per periode | Skor tersedia T+1 hari | Target & KPI Module
BG-08 | Mempercepat pemahaman dokumen tender via AI | Waktu rata-rata staf membaca dokumen RKS/LPHS turun signifikan | Ringkasan AI < 30 detik | AI Integration Architecture, AI Features

## GAP_TRACEABILITY
KINETIC CRM — GAP TRACEABILITY MATRIX
22 Gaps from BA Review (4 Critical, 7 Major, 5 Minor, 6 Future) ¦ From Doc 003
Gap ID | Classification | Gap Description | Business Impact | Resolution Docs | Status
GAP01 | Critical | Tidak ada modul Target & KPI | Sistem hanya alat administrasi, bukan monitoring performa | 043, 044, 045 | 100% resolved
GAP02 | Critical | Tidak ada Menu Configuration - semua parameter hardcode | Setiap perubahan butuh deployment ulang | 027-031 | 100% resolved
GAP03 | Critical | Question Type di localStorage, bukan DB | Data hilang saat clear browser | 024, 061 | 100% resolved
GAP04 | Critical | Tidak ada mekanisme cancel proyek | Data pipeline tidak akurat, proyek zombie | 033, 038 | 100% resolved
GAP05 | Major | Hierarki organisasi tidak dimodelkan | Laporan per unit tidak akurat | 015 | 100% resolved
GAP06 | Major | Tidak ada SLA enforcement pada approval | Deadline tender terlewat | 041, 029 | 100% resolved
GAP07 | Major | Tidak ada mekanisme re-assign approval | Proyek stuck jika approver tidak aktif | 042 | 100% resolved
GAP08 | Major | Review departemen tidak paralel dengan PM | Cycle time lebih panjang | 035, 040 | 100% resolved
GAP09 | Major | Kompetitor sebagai JSON bebas, tidak ada Master | Analisis kompetitor lintas proyek tidak mungkin | 023, 036 | 100% resolved
GAP10 | Major | Dashboard tidak filter per cabang/divisi/periode | Management tidak bisa drill-down | 050 | 100% resolved
GAP11 | Major | Tidak ada laporan periodik export Excel/PDF | Laporan ke direksi manual | 051 | 100% resolved
GAP12 | Minor | Tidak ada field alasan kekalahan terstruktur | Analisis kenapa kalah tidak agregat | 026, 037 | 100% resolved
GAP13 | Minor | Tidak ada notifikasi deadline approaching | Cabang dan PM lupa deadline | 046 | 100% resolved
GAP14 | Minor | Tidak ada versioning dokumen | Reviewer baca dokumen outdated | 049 | 100% resolved
GAP15 | Minor | Tidak ada health check endpoint | Monitoring infrastruktur terbatas | 060 | 100% resolved
GAP16 | Minor | Tidak ada export audit log | Compliance audit terhambat | 052 | 100% resolved
GAP17 | Future | Tidak ada integrasi SSO | User kelola password terpisah | 009, 064 | Fase 2
GAP18 | Future | Tidak ada notifikasi email/WhatsApp eksternal | User yang tidak buka sistem tidak tahu | 047 | Fase 2/3
GAP19 | Future | Tidak ada approval via link one-click | Management harus login untuk approve | 047 | Fase 2
GAP20 | Future | Tidak ada analitik kompetitor lintas proyek | Tidak tahu kompetitor yang sering menang | 023, 064 | Fase 3
GAP21 | Future | Tidak ada integrasi kontrak pasca-tender | Proses kontrak kembali manual | 064 | Fase 3
GAP22 | Future | Tidak ada mobile app/PWA | Management kesulitan approve via mobile | 058, 064 | Fase 3

## API_ENDPOINTS
KINETIC CRM — API ENDPOINT CATALOG
Total: 81 Endpoints ¦ Base URL: /api/v1 ¦ From Doc 057
Module | Method | Endpoint | Auth Required | Description
Authentication
Authentication | POST | /api/v1/auth/forgot-password | All | Request reset password via email
Authentication | POST | /api/v1/auth/reset-password | All | Reset password dengan token
Authentication | POST | /api/v1/auth/logout | Auth | Logout, invalidate session
Users
Users | POST | /api/v1/users | Admin | Buat user baru
Users | GET | /api/v1/users/:id | Admin | Detail user
Users | PUT | /api/v1/users/:id | Admin | Update user
Users | PUT | /api/v1/users/:id/reset-password | Admin | Reset password user
Users | PUT | /api/v1/users/:id/lock | Admin | Lock/Unlock user
Prospects
Prospects | POST | /api/v1/prospects | Cabang,Admin | Buat prospek baru
Prospects | GET | /api/v1/prospects/:id | Auth | Detail prospek + review history
Prospects | PUT | /api/v1/prospects/:id | Cabang,Admin | Update draft prospek
Prospects | DELETE | /api/v1/prospects/:id | Cabang,Admin | Soft-delete (hanya prospecting)
Prospects | POST | /api/v1/prospects/:id/submit | Cabang,Admin | Submit ke PM
Prospects | POST | /api/v1/prospects/:id/approve | PM,Admin | PM approve prospek
Prospects | POST | /api/v1/prospects/:id/revise | PM,Admin | PM kirim pertanyaan revisi
Prospects | POST | /api/v1/prospects/:id/answer | Cabang,Admin | Cabang jawab revisi
Prospects | POST | /api/v1/prospects/:id/convert | Cabang,Admin | Konversi ke proyek
Projects
Projects | POST | /api/v1/projects | Cabang,Admin | Buat proyek baru
Projects | GET | /api/v1/projects/:id | Auth | Detail proyek lengkap
Projects | PUT | /api/v1/projects/:id | Cabang,Admin | Update info dasar proyek
Projects | POST | /api/v1/projects/:id/cancel | PM,Admin | Cancel proyek
RKS
RKS | POST | /api/v1/projects/:id/rks | Cabang,Admin | Input/Update data RKS
RKS | POST | /api/v1/projects/:id/rks/submit | Cabang,Admin | Submit RKS ke PM
RKS | POST | /api/v1/projects/:id/rks/approve | PM,Admin | PM approve RKS
RKS | POST | /api/v1/projects/:id/rks/revise | PM,Admin | PM kirim revisi RKS
LPHS/SIOS
LPHS/SIOS | POST | /api/v1/projects/:id/lphs | Cabang,Admin | Upload draft LPHS
LPHS/SIOS | POST | /api/v1/projects/:id/lphs/submit | Cabang,Admin | Submit ke Dept Review
LPHS/SIOS | POST | /api/v1/projects/:id/lphs/dept-approve | Dept,Admin | Departemen approve LPHS
LPHS/SIOS | POST | /api/v1/projects/:id/lphs/pm-approve | PM,Admin | PM approve LPHS
LPHS/SIOS | POST | /api/v1/projects/:id/lphs/mgmt-approve | Mgmt,Admin | Management approve LPHS
LPHS/SIOS | POST | /api/v1/projects/:id/lphs/revise | PM,Dept,Mgmt | Revisi tertarget per departemen
Harga
Harga | POST | /api/v1/projects/:id/harga | Cabang,Admin | Input harga penawaran
Kompetitor
Kompetitor | POST | /api/v1/projects/:id/competitors | Cabang,Admin | Tambah kompetitor
Pemenang
Pemenang | POST | /api/v1/projects/:id/pemenang | Cabang,Admin | Input hasil tender (menang/kalah)
Delivery
Delivery | POST | /api/v1/projects/:id/delivery | Cabang,Admin | Input target delivery
Approvals
Approvals | POST | /api/v1/approvals/:id/approve | Auth | Approve
Approvals | POST | /api/v1/approvals/:id/revise | Auth | Revisi/Reject
Master Data
Master Data | POST | /api/v1/master/customers | Admin | Buat customer
Master Data | GET | /api/v1/master/competitors | Admin | List kompetitor master
Master Data | POST | /api/v1/master/competitors | Admin | Buat kompetitor
Master Data | GET | /api/v1/master/project-statuses | Admin | List status proyek
Master Data | GET | /api/v1/master/document-types | Admin | List tipe dokumen
Master Data | GET | /api/v1/master/questions | Admin | List pertanyaan master
Master Data | GET | /api/v1/master/holidays | Admin | List hari libur
Master Data | GET | /api/v1/master/loss-reasons | Admin | List alasan kekalahan
Dashboard
Dashboard | GET | /api/v1/dashboard/charts | Auth | Data chart dashboard
Reports
Reports | GET | /api/v1/reports/pipeline | Auth | Laporan Pipeline
Reports | GET | /api/v1/reports/progress-target | Auth | Laporan Progress vs Target
Reports | GET | /api/v1/reports/export | Auth | Export laporan ke Excel/PDF
Notifications
Notifications | PUT | /api/v1/notifications/:id/read | Auth | Tandai sudah dibaca
Notifications | PUT | /api/v1/notifications/read-all | Auth | Tandai semua sudah dibaca
Audit
Audit | GET | /api/v1/audit-logs/export | Admin | Export audit log ke CSV
Documents
Documents | GET | /api/v1/documents/:id/download | Auth | Download dokumen
AI
AI | POST | /api/v1/ai/analyze-prospect | Auth | Analisis prospek via AI
AI | POST | /api/v1/ai/competitor-insight | Auth | Insight kompetitor via AI
AI | POST | /api/v1/ai/kpi-insight | Auth | Insight KPI via AI
Configuration
Configuration | PUT | /api/v1/config/:module | Admin | Update konfigurasi module
Target & KPI
Target & KPI | POST | /api/v1/targets | Admin,Mgmt | Buat/update target
Target & KPI | GET | /api/v1/kpi/scores | Auth | Skor KPI per unit organisasi
Target & KPI | GET | /api/v1/kpi/progress | Auth | Progress real-time vs target
Health
Health | GET | /api/v1/health | Public | Health check endpoint

## DATABASE_SCHEMA
KINETIC CRM — DATABASE SCHEMA OVERVIEW
Total: 43 Tables ¦ MySQL/InnoDB ¦ From Docs 053, 054
Domain | Table Name | Description | Key Columns
Organizations
Organizations | divisions | Divisi di bawah perusahaan | id, company_id, name, code, description, is_active
Organizations | departments | Departemen fungsional | id, division_id, name, code, description, is_active
Organizations | branches | Cabang operasional geografis | id, division_id, name, code, address, city, phone, email, is_active
Access
Access | roles | Role definitions | id, name, code, description, is_system, is_active
Access | permissions | Permission definitions | id, module, action, code, description
Access | role_permissions | Role-permission mapping | role_id, permission_id
Access | positions | Job positions | id, department_id, name, code, level, is_active
Master Data
Master Data | industries | Industri master | id, name, code, is_active
Master Data | project_categories | Kategori proyek | id, name, code, requires_rks, requires_lphs, is_active
Master Data | project_statuses | Status proyek dinamis | id, code, label, color_hex, sort_order, is_terminal, is_active
Master Data | document_types | Tipe dokumen | id, name, code, description, is_active
Master Data | competitors | Kompetitor master | id, name, code, description, is_active
Master Data | questions | Pertanyaan master | id, question_type_id, text, is_required, sort_order, is_active
Master Data | question_types | Tipe pertanyaan | id, name, code, input_type, options, is_active
Master Data | holidays | Hari libur | id, date, name, year, is_active
Master Data | loss_reasons | Alasan kekalahan | id, name, code, description, is_active
Master Data | periods | Periode pelaporan | id, name, start_date, end_date, is_active
Core
Core | prospect_pm_reviews | Riwayat review PM prospek | id, prospect_id, review_round, pm_user_id, status
Core | prospect_review_questions | Pertanyaan review prospek | id, review_id, question_text, answer_text
Core | projects | Data proyek inti | id, project_code, name, type, status_id, branch_id, customer_id, category_id
Core | project_rks | Data RKS proyek | id, project_id, tender_number, deadline_tender, status
Core | project_rks_reviews | Riwayat review RKS | id, rks_id, review_round, pm_user_id, status
Core | project_lphs | Data LPHS/SIOS proyek | id, project_id, overall_status, pm_status, mgmt_status
Core | project_lphs_dept_reviews | Review departemen LPHS | id, lphs_id, department_id, reviewer_id, status
Core | project_harga | Harga penawaran | id, project_id, total_price, notes
Core | project_competitors | Kompetitor per proyek | project_id, competitor_id, competitor_name, notes
Core | project_pemenang | Hasil tender | id, project_id, is_win, loss_reason_id, loss_notes
Core | project_delivery | Target delivery | id, project_id, target_date, actual_date, status
Core | project_documents | Dokumen proyek | id, project_id, doc_type, file_name, file_path, version
Core | project_timeline_events | Timeline event | id, project_id, event_type, event_description, actor_user_id
Workflow
Workflow | approval_decisions | Keputusan approval | id, request_id, decision, decision_notes, decided_by
Workflow | workflow_stages | Tahap workflow | id, name, position, approver_role, is_active
Target & KPI
Target & KPI | kpi_targets | Target KPI per periode | id, kpi_id, period_id, branch_id, target_value, version
Target & KPI | kpi_scores | Skor KPI aktual | id, kpi_id, period_id, branch_id, actual_value, score
Notification
Config
Audit
Audit | audit_logs | Audit log append-only | id, user_id, action, entity_type, entity_id, payload_before, payload_after

## SPRINT_PLAN
KINETIC CRM — SPRINT & MILESTONE PLAN
Timeline: 3 Juni - 31 Juli 2026 (Revisi: 22 Juni)
Sprint | Tanggal | Milestone | Key Deliverables | Planned Progress | Status
W1 | 22-29 Jun | Foundation & Scaffolding | Vite+React19, TS, Tailwind, Docker, Routing, Atomic UI, Auth UI, Zustand Stores, API Client | 38% | AHEAD
W2 | 30 Jun-6 Jul | Core Frontend Integration | Prospek, Proyek, Approval UI, Master Data CRUD, Config Pages, Reports, Dashboard charts | Planned | PLANNED
W3 | 7-13 Jul | Advanced Features + Backend Start | KPI Dashboard, Notifications, Profile, Error Pages, Backend API Server setup | Planned | PLANNED
W4 | 14-20 Jul | Backend API + DB Integration | Auth API, CRUD Endpoints, Prisma+MySQL, Real API Login, Frontend-BE Integration | Planned | PLANNED
W5 | 21-31 Jul | Final Integration + Testing | All Endpoints, Unit Tests, Integration Tests, Deployment, Launch Prep | Planned | PLANNED

## MODULE_DEPENDENCY
KINETIC CRM — MODULE DEPENDENCY MATRIX
Dependencies between modules for implementation ordering
Module | Depends On | Required By | Priority
Infrastructure (Vite/Docker) | - | All Frontend modules | P1
UI Components | Infrastructure | All page modules | P1
Routing & Guards | Infrastructure, UI | All page modules | P1
Authentication | Infrastructure | All modules (login required) | P1
State Management (Zustand) | Infrastructure | All page modules | P1
Service Layer (API Client) | Infrastructure | All API integration | P1
Organization Hierarchy | - | User Management, Branch scoping | P1
Position Management | Organization Hierarchy | Approval Engine | P1
Role & Permission | Organization Hierarchy | Authorization, Navigation | P1
User Management | Organization, Role, Position | All modules (user context) | P1
Master Customer & Category | - | Prospect, Project | P1
Master Status & Document Type | - | Project, Document Management | P1
Master Competitor | - | Harga & Kompetitor module | P2
Master Question & Type | - | Prospect, RKS questionnaire | P1
Master Period & Holiday | - | SLA Engine, KPI | P2
Master Loss Reason | - | Pemenang & Delivery | P2
Configuration (CFG-01~14) | Organization, Master Data | All modules (config-driven) | P1
Prospect Management | Customer, User, Config | Project Core (conversion) | P1
Project Core | Customer, Category, Status, Config | RKS, LPHS, Harga, Pemenang | P1
RKS Module | Project Core, Question | LPHS/SIOS | P1
LPHS/SIOS Module | RKS, Approval Engine | Harga, Pemenang | P1
Harga & Kompetitor | Project Core, Competitor | Pemenang | P1
Pemenang & Delivery | Project Core, Loss Reason | Reporting, KPI | P1
Project Cancellation | Project Core | Reporting | P1
Approval Engine Core | User, Role, Position, Config | Prospect, RKS, LPHS approvals | P1
Parallel Review & Revision | Approval Engine | LPHS/SIOS | P1
SLA & Escalation Engine | Approval Engine, Period, Holiday | Notifications | P1
Backup Approver | Approval Engine, Config | Reassignment feature | P1
Target & KPI | KPI Indicators, Period, Config | Dashboard, Reporting | P1
In-App Notification | User, Config | All modules (notifications) | P1
Document Upload & Storage | Document Type | Prospect, Project, RKS, LPHS | P1
Document Versioning | Document Upload | Audit Trail | P1
Dashboard | All core modules, KPI | Management reporting | P2
Reporting | All core modules, KPI | Management reporting | P2
Audit Trail | All modules (append-only) | Compliance, export | P1
Backend API Server | Database, Auth, All modules | Frontend integration | P1
Testing | All modules | Deployment, Launch | P1

## FEATURE_CHECKLIST
KINETIC CRM — FEATURE CHECKLIST
Checklist lengkap semua fitur berdasarkan dokumentasi MD
No | Module | Feature / Task | Doc Ref
Infrastructure
1 | Infrastructure | Vite + React 19 + TypeScript Setup | 006
2 | Infrastructure | Tailwind CSS v4 Configuration | 006
3 | Infrastructure | Docker Compose (6 services) | 060
4 | Infrastructure | Nginx Reverse Proxy Config | 060
5 | Infrastructure | Environment Variables Setup | 060
UI Components
6 | UI Components | 12 Atomic Components (Badge, Button, Card, etc.) | 058
7 | UI Components | 7 Layout Components (AppLayout, Sidebar, etc.) | 058
8 | UI Components | 10 Shared Components (DataTable, FilterPanel, etc.) | 058
Routing & Guards
9 | Routing & Guards | 50+ Routes (Lazy Loaded) | 012
10 | Routing & Guards | ProtectedRoute Guard | 020
11 | Routing & Guards | GuestRoute Guard | 020
12 | Routing & Guards | RoleRoute Guard | 020
13 | Routing & Guards | PermissionRoute Guard | 020
14 | Routing & Guards | Permission-Based Navigation | 012
Authentication
15 | Authentication | Login Page UI | 019
16 | Authentication | Forgot Password UI | 019
17 | Authentication | Reset Password UI | 019
18 | Authentication | Auth Store (Zustand + Persist) | 006
19 | Authentication | JWT Interceptor | 019
20 | Authentication | Real API Login | 019
State Management
21 | State Management | 12 Zustand Stores (auth, project, prospect, etc.) | 006
22 | State Management | React Query Hooks (11 modules) | 006
Service Layer
23 | Service Layer | API Client (Axios + JWT) | 006
24 | Service Layer | 15 Service Files (API definitions) | 057
25 | Service Layer | Mock Data for Development | 006
Prospect Module
26 | Prospect Module | List Prospek (Table + Mobile Card) | 032
27 | Prospect Module | Detail Prospek (Overview + Tabs) | 032
28 | Prospect Module | Form Prospek (Existing/New Customer) | 032
29 | Prospect Module | Workflow Prospek (7 stages lifecycle) | 032
30 | Prospect Module | Questionnaire Integration | 024
31 | Prospect Module | Prospect Backend API Integration | 032
Project Module
32 | Project Module | List Proyek (Table + Stats Cards) | 033
33 | Project Module | Form Proyek (Create/Edit) | 033
34 | Project Module | Detail Proyek (10 Tabs) | 033
35 | Project Module | Tab: Overview | 033
36 | Project Module | Tab: RKS | 034
37 | Project Module | Tab: Review RKS | 034
38 | Project Module | Tab: LPHS/SIOS | 035
39 | Project Module | Tab: Harga | 036
40 | Project Module | Tab: Kompetitor | 036
41 | Project Module | Tab: Pemenang | 037
42 | Project Module | Tab: Delivery | 037
43 | Project Module | Tab: Timeline | 033
44 | Project Module | Tab: Dokumen | 048
45 | Project Module | Tab: Chat (Mock) | 058
46 | Project Module | Dynamic Stepper (Workflow) | 013
47 | Project Module | Project Backend API Integration | 033
Approval Module
48 | Approval Module | Approval Inbox Page | 039
49 | Approval Module | Review Drawer (Approve/Reject) | 039
50 | Approval Module | SLA Badge & Timer | 041
51 | Approval Module | 3-Group Filter (Pending/My Turn/Completed) | 039
52 | Approval Module | Approval Backend API Integration | 039
Master Data
53 | Master Data | Customer CRUD | 021
54 | Master Data | Competitor CRUD | 023
55 | Master Data | Category CRUD | 021
56 | Master Data | Document Type CRUD | 022
57 | Master Data | Question CRUD | 024
58 | Master Data | Holiday CRUD | 025
59 | Master Data | Loss Reason CRUD | 026
60 | Master Data | Project Status CRUD | 022
61 | Master Data | Period CRUD | 025
Configuration
62 | Configuration | CFG-01: Organization Config | 027
63 | Configuration | CFG-02: Approval Workflow Builder | 027
64 | Configuration | CFG-03: Status Proyek Config | 028
65 | Configuration | CFG-04: Role & Permission Config | 028
66 | Configuration | CFG-05: SLA Config | 029
67 | Configuration | CFG-06: Reminder/Escalation Config | 029
68 | Configuration | CFG-07: Target & Bobot KPI Config | 030
69 | Configuration | CFG-08: Dashboard Widget Config | 030
70 | Configuration | CFG-09: Notification Email Config | 030
71 | Configuration | CFG-10: Period Config | 031
72 | Configuration | CFG-11: Kategori Proyek Config | 028
73 | Configuration | CFG-12: Question Type Config | 031
Reports & Dashboard
74 | Reports & Dashboard | Dashboard per Role with Filter Granular | 050
75 | Reports & Dashboard | Win/Loss Report | 051
76 | Reports & Dashboard | Pipeline Report | 051
77 | Reports & Dashboard | Progress vs Target Report | 051
78 | Reports & Dashboard | Export Excel/PDF | 051
79 | Reports & Dashboard | AI Executive Summary Widget | 011
Users & Audit
80 | Users & Audit | User CRUD + Zod Validation | 018
81 | Users & Audit | Audit Log Page + Detail | 052
82 | Users & Audit | Audit Log Export CSV | 052
Notifications
83 | Notifications | In-App Notification Store | 046
84 | Notifications | Notification Bell + Badge Counter | 046
Other
85 | Other | Profile Page | 018
86 | Other | Error Pages (403, 404, 500) | 059
87 | Other | GlobalSearch in Topbar | 014
Backend
88 | Backend | API Server (Node.js + Express) | 056
89 | Backend | Database (Prisma + MySQL) | 054
90 | Backend | Authentication API (JWT) | 019
91 | Backend | All CRUD Endpoints | 057
92 | Backend | Redis + Scheduler | 041
Testing
93 | Testing | Unit Tests (critical path) | 062
94 | Testing | Integration Tests | 062
95 | Testing | E2E Tests | 062

## DESIGN_PRINCIPLES
KINETIC CRM — DESIGN PRINCIPLES
8 Prinsip Desain Utama ¦ From Doc 001
# | Principle | Description
1 | No Hardcode Parameters | Setiap nilai yang mungkin berubah karena keputusan bisnis harus dikonfigurasi via Modul Configuration (CFG-01 s/d CFG-14)
2 | No JSON Blobs | Setiap data yang berpotensi dianalisis/dihitung/dilaporkan harus berada dalam tabel relasional dengan kolom dan tipe data yang jelas
3 | Audit-by-Design | Setiap aksi mutasi data (create/update/delete/approve/reject) tercatat otomatis di audit log; logging bukan fitur tambahan
4 | Position-Based Approval | Konfigurasi siapa yang approve didasarkan pada jabatan/posisi struktural, bukan nama individu
5 | Explicit State Machine | State machine eksplisit dengan precondition enforcement di backend; frontend bukan satu-satunya penjaga aturan
6 | AI as Architecture Layer | Seluruh akses AI melalui AI Service Layer yang provider-agnostic; business module tidak boleh panggil Gemini langsung
7 | Optimistic Locking | Optimistic locking untuk mencegah race condition pada entitas yang dapat diedit bersamaan
8 | Gap Traceability | Setiap gap diselesaikan secara desain, dilacak melalui Gap Traceability Matrix (003), tidak ada gap tanpa resolusi

## STAKEHOLDERS
KINETIC CRM — STAKEHOLDER & ACTOR MATRIX
From Doc 001 Section 6
Actor | Category | Main Involvement | Key Actions
Staf Cabang | Pengguna Operasional | Input data prospek, RKS, harga, kompetitor, hasil tender, delivery | Create prospect, Fill RKS, Input harga, Upload LPHS draft, Input hasil tender
Project Manager (PM) | Operasional / Approver | Review & approval prospek, RKS, koordinasi LPHS lintas departemen | Approve/Reject prospect, Approve RKS, Review LPHS, Cancel project
Staf Departemen Teknis | Approver Spesialis | Review LPHS/SIOS sesuai bidang (Engineering, Legal, Finance, dll.) | Review & approve/reject LPHS dept section
Management | Approver Eksekutif | Approval final LPHS, monitoring dashboard, evaluasi performa unit | Final approve LPHS, View dashboard, Set targets
Administrator (IT/Admin) | Pengelola Sistem | Master data, konfigurasi sistem, user/role management, audit | Manage config, Users, Master data, View audit logs
Direktur Regional | Approver Eksekutif | Role baru yang bisa ditambahkan tanpa coding (validasi desain dinamis) | Configurable via Role & Permission module
Tim Pengembang (FE/BE/DB) | Internal | Pembangun sistem, konsumen dokumentasi | Implementasi berdasarkan spec dokumen
QA Engineer | Internal | Penjamin kualitas, konsumen Master Test Case Catalog | Execute test cases from doc 062
Project Manager IT | Internal | Perencana, konsumen Sprint Planning | Plan sprints from doc 063